## Page1_Features
Page | Priority | user route stage | Category | Feature | UI Type | Description | Default State | Required Data | Interaction Logic | Build Status | Notes | Assistant Review | Problem / Risk | Missing Info | Decision Required | Advice / Recommendation | my comment | my descision
Page 1 | MVP | 0 | instructions + constraints | [6 empty] | Required |  | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple. | Good | keep
Page 1 | MVP | 1 | Navigation | Country selector | Dropdown | Select focal country. | Default country Germany | country_name / country_code | Reload profile, family, tradeoff highlights, trajectories | Required | Use sidebar; keep visible at all times Flag countries - archetypes (6 mvp) | Streamlit-friendly and stable. | None. | Default country not finalized. | Choose opening country. | Germany or Poland are good demo defaults. | germany (it is in the defalt state - you didn’t read thorowly!!!) | germany
Page 1 | MVP | 3 or 6? | Comparison | Compare 2 countries | Dropdown + optional toggle | Add one comparator country only. | OFF by default; comparator = none | country_name / selected comparator | Overlay comparator in charts and profile summary | Required | Do not allow 3+ countries in MVP | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple. | advise stage 3 or 6?
Page 1 | MVP | 1 | Reference | EU-relative normalization | Toggle / default mode | Show values relative to EU average. Or country relative avg. | ON by default | eu_relative_kpi_table | All KPI cards/charts show EU-relative index or difference | Required | Absolute/raw toggle is Priority 1 | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple. |  | eu avg defalt, country avg by toggle
Page 1 | MVP | 4 | Identity | Structural family display | Badge/cards | Show selected country family: Innovation-Core, Industrial/Transition, Adaptive/Peripheral., top 3 related strategy, top 3 other countries?, sub family? | Auto from selected country | country_family_metadata | Update badge and short explanation | Required | Use family colors consistently | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple. | in country card
Page 1 | MVP | 2 | Profile | Country profile summary | Summary cards -dimentions + investment profile | Show structural identity, key KPI/dimentions positions, investment profile,top 1 main tension. May need also absolut values??? Text should appear in the summary cell… | Auto from selected country | country_profile_summary | Update on country selection | Required | Keep compact; no dense table suggest to have same table for other country comparrison… so button above and next to it other country column - highloght other country also on graphs… maybe colored and highlited on eu map??? | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple. | predefined cards (no relatice comparrison, add family and invest profile)
Page 2 | MVP | 2 | profile | time series plot… | drop down? | time series plot of chosen dimension | growth? |  |  | Required | maybe instead of another dropdown - use the tradeoff vectors xy from fig5?? And show both? | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple. | must show dimensions vs time in page1 | add - help define better.
Page 1 | MVP | 5 | Tradeoffs | Tradeoff scatter maps | Plotly scatter | Main 2D map. X/Y chosen from curated tradeoff pairs. How to make sure takes suggested couples - maybe dropdown mvp only couples? | Default tradeoff TBD: Innovation vs Emissions or Growth vs Inequality | tradeoff_export_table | Highlight selected country and comparator; color by family | Required | This is core Page 1 visual how to track the tradeoffs and investigations?? Tracker in this page too ?? | Core differentiator. Strong MVP choice. | Too many tradeoff combinations may overwhelm UX. | Exact 3–5 MVP tradeoffs not frozen. | Freeze curated tradeoff list. | Do NOT allow arbitrary x/y KPI selection in MVP. | only tradeof pairs - need to define together - advise and add to tasks | TBD brainstorm task
Page 1 | MVP | 5 | Tradeoffs | Multi-tradeoff explorer | Dropdown / segmented control | Choose among 3–5 predefined tradeoff spaces. | Default first tradeoff | tradeoff_config_table | Change x/y/chart title/quadrant labels | Required | Do not expose arbitrary x/y in MVP | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple. |  | add - help define better.
Page 1 | MVP | 5 | Pathways | Time trajectory lines | Line chart | Show selected KPI/tradeoff movement over time. | Default 2014-latest range | country_year_kpi_panel | Update country/comparator/time series | Required | Use as historical grounding | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple. |  | add - help define better.
Page 1 | MVP | 6 | Interpretation | Quadrant explanations | Text card linked to selected tradeoff | Explain what high/low x and y mean. | Auto from selected tradeoff | tradeoff_config_table | Update explanation when tradeoff changes | Required | Prevents fake interpretation can appear in the AI placeholder - get feel… | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple. |  | TBD brainstorm task
Page 2 | MVP | 7 | next | button-next | button-next | 3 options: *further investigations *tostratigic exploration reset all |  |  |  |  | may be 3 buttons???? | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple. | advise - 1 or 3 buttons | TBD brainstorm task
Page 1 | MVP | 0 | Methodology | Assumptions panel | Expander | Explain non-causal framing, normalization, missingness, limits. | Collapsed by default | static methodology text | No dynamic dependency | Required | Credibility layer | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple. |  | keep
Page 1 | MVP | 0 | UX | Guided layout | Page layout | see user rout stage column and tab! | Fixed route | N/A | User follows top-to-bottom logic | Required | No generic BI grid follow the numbers near each stage | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple. |  | keep
|  |  |  | overall change index?? | [7 empty] | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple. |  | suggest how and add to final tables
Page 1 | Priority 1A | is it needed??? | Reference | Absolute/raw toggle not sure to raw, probably to country avg only - raw may be required at the country card.. | Toggle | Switch EU-relative view to raw values. | OFF by default | raw_kpi_table + eu_relative_kpi_table | Switch cards/charts units | Optional | Transparency upgrade | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple. | you didn’t read all cells! I asked if remove or keep | remove
Page 1 | Priority 1A | add to 2 | Credibility | Evidence confidence layer | Badge / traffic light | Show confidence for selected interpretation. | Visible on interpretation cards | confidence_metadata_table | Update by feature/tradeoff | Optional | Good DA credibility easy, but do we have the estimation??? | Good credibility feature. | Cannot fake statistical certainty. | Confidence scoring methodology. | Simple rule-based or remove. | Use exploratory/moderate/strong tags only. | need development session and add to tables later | TBD brainstorm task
Page 1 | Priority 1A | 0 - mvp | UX | Educational onboarding | Intro box / expander | Explain how to use the page in 3 steps. | Collapsed or small banner | static onboarding text | No dynamic dependency | Optional | Useful for teachers/investors | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple. |  | keep
Page 1 | Priority 1B | add to 4 family? | Topology | Cluster/topology map | Scatter / map-like plot | Show structural positioning by family/cluster. | Hidden in separate section/tab | cluster_export_table | Highlight selected country/comparator | Optional | Signature visual but not MVP | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple. |  | keep
Page 1 | Priority 1A | add to 2 card | Data Dimension | Energy dependency dimension | KPI/card + optional chart | Add energy profile/dependency if data is clean. | Hidden until data validated | energy_dependency_table | Add to profile/tradeoff/shock context | Optional | Only if easy data integration probably low priority - moved from 1A | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple. | advise on complexity | move to lower priority
Page 1 | Priority 1B | isnt it 5? | Pathways | Pathway vector arrows | Arrow overlay on scatter | Show directional movement from earlier to later period. | OFF by default | trajectory_vectors_table | Draw arrows for selected country/comparator | Optional | Use carefully; avoid clutter | Visually strong but risky. | Can create clutter and false direction interpretation. | Arrow time-window logic. | Keep P1 or remove from capstone. | Only show for selected country. |  | move to lower priority
Page 1 | Priority 1C | tbd | Export | Export/share summary | Button | Download current selection summary. | OFF/no default | selected state + summary text | Save PNG/CSV/markdown summary | Optional | instead - can prepare a downloadable print screen of country card… | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple. | only if time | higher priority but not mvp
Page 1 | Priority 1C | tbd | Identity | Archetype refinement | Badge/text | Show sub-family/archetype below main family. | Hidden or secondary | archetype_metadata_table | Update with country | Optional | Needs careful wording | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple.
[11 empty] | WTF!!! | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple.
[11 empty] | WTF!!! | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple.
[11 empty] | WTF!!! | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple.
[11 empty] | WTF!!! | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple.
[11 empty] | WTF!!! | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple.
[11 empty] | WTF!!! | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple.
[11 empty] | WTF!!! | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple.
[11 empty] | WTF!!! | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple.
[11 empty] | WTF!!! | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple.
[11 empty] | WTF!!! | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple.
[11 empty] | WTF!!! | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple.
[11 empty] | WTF!!! | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple.
[12 empty] | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple.
[12 empty] | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple.
[12 empty] | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple.
[12 empty] | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple.
[12 empty] | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple.
[12 empty] | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple.
[12 empty] | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple.
[12 empty] | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple.
[12 empty] | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple.
[12 empty] | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple.
[12 empty] | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple.
[12 empty] | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple.
[12 empty] | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple.
[12 empty] | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple.
[12 empty] | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple.
[12 empty] | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple.
[12 empty] | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple.
[12 empty] | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple.
[12 empty] | Looks structurally reasonable. |  |  |  | Keep interaction hierarchy simple.

## Page2_Features
Page | Priority | user route stage | Category | Feature | UI Type | Description | Default State | Required Data | Interaction Logic | Build Status | Notes | Assistant Review | Problem / Risk | Missing Info | Decision Required | Advice / Recommendation | my comment | my descision
Page 2 | MVP | 0 | landing | explanation box | [7 empty] | Generally feasible in Streamlit. |  |  |  | Prefer guided step flow over dashboard layout. |  | keep
Page 2 | MVP | 0 | landing | continue from page 1? Or select country | [7 empty] | Generally feasible in Streamlit. |  |  |  | Prefer guided step flow over dashboard layout. | once select in page 1 auto select too in page 2.. Only country, once reset --> defalt germany?? | TBD discussion complexity
Page 2 | MVP | 1 | Baseline | Current structural profile | Summary cards | Show selected country's baseline before scenario. Take same as in page 1 - - use the "another country" column to before-after… | Default country same as Page 1 or Germanyif not continue.. TBD! | country_profile_summary / baseline_state | Feeds before/after comparison | Required | Must orient user before/agter sliders after appears only after "run" button.. | Generally feasible in Streamlit. |  |  |  | Prefer guided step flow over dashboard layout. | use kpi table as in page 1. but instead of the "other" country - use extra column for"after" | keep
Page 2 | MVP | 3 | Strategy | Objective selector | Dropdown / radio buttons one at a time | Choose strategic objective: balanced, innovation, sustainability, resilience. | Balanced | objective_config_table | Sets weighting emphasis and explanation | Required | Keep to 3–4 objectives | Generally feasible in Streamlit. |  |  |  | Prefer guided step flow over dashboard layout. |  | keep
Page 2 | MVP | 2 | Reference | Reference-system selector | present also the number% | Compare to EU average or selected country avg. | EU average | reference_profiles_table | Switch target/reference line or profile | Required | country avg ref or (Family reference future) TBD | Generally feasible in Streamlit. |  |  |  | Prefer guided step flow over dashboard layout. |  | EU avg defalt <> country avg ref
Page 2 | MVP | 4 | Interaction | Investment-priority sliders | Sliders + type %? | Adjust emphasis across dimensions. must contain also investment profile ref - so ref vs test 2 columns.. must summ to 100% | real ref status | slider_config_table | Normalize weights; feed directional shift | Required | Do not imply causal impact need reset to defalt separate button? | Central Page 2 interaction. | May imply fake simulation. | Directional shift logic not frozen. | Define exactly what sliders modify. | Use wording: exploratory directional adjustment. | current investment profile ref and test new investment profile slider | keep
Page 2 | MVP | 6 | run - calculate | run button | button | [6 empty] | Generally feasible in Streamlit. |  |  |  | Prefer guided step flow over dashboard layout. |  | keep
Page 2 | MVP | 7 | Output | Before/after comparison | Plot - start-end graph? should be shown on all dimensins | Show current vs adjusted delta. | Baseline shown before run | scenario_output_table | Update after Run button | Required | Core learning loop | Generally feasible in Streamlit. |  |  |  | Prefer guided step flow over dashboard layout. |  | keep!
Page 2 | MVP | 7 | Output | Before/after comparison | Plot - start-end scatter graph? X-y tradeoff space + arrow | Show current vs adjusted direction. | Baseline shown before run | scenario_output_table | Update after Run button | Required | Core learning loop | Generally feasible in Streamlit. |  |  |  | Prefer guided step flow over dashboard layout. |  | keep
Page 2 | MVP | 7 | Output | Before/after comparison | compare to chosen archetypes?? | [6 empty] | Generally feasible in Streamlit. |  |  |  | Prefer guided step flow over dashboard layout. |  | TBD discussion complexity
Page 2 | lower priority? But place holder? | 5? | Shocks | Energy shock | Toggle/button | Apply simplified energy stress scenario. | OFF | shock_config_table / energy indicators | Modify interpretation/output with stress factor | Required if current shock logic exists | Fallback: narrative-only shock choose shock strenght? | Good educational framing. | Shock logic may become pseudo-modeling. | Narrative vs numeric shock definition. | Freeze simplified logic. | Rule-based shocks are safer than numeric forecasting. |  | rule based - simplified mvp
Page 2 | lower priority? But place holder? | 5? | Shocks | Recession shock | Toggle/button | Apply simplified downturn scenario. | OFF | shock_config_table / macro indicators | Modify interpretation/output with stress factor | Required if current shock logic exists | Fallback: narrative-only shock | Good educational framing. | Shock logic may become pseudo-modeling. | Narrative vs numeric shock definition. | Freeze simplified logic. | Rule-based shocks are safer than numeric forecasting. |  | rule based - simplified mvp
Page 2 | MVP | 7 | Interpretation | Tradeoff explanations | Text card | Explain directional tensions created by scenario. | Hidden until run | rule_based_interpretation_table | Update after Run | Required | Rule-based, not LLM | Generally feasible in Streamlit. |  |  |  | Prefer guided step flow over dashboard layout. |  | keep for mvp
Page 2 | MVP | 0 | Methodology | Assumptions panel | Expander | Explain non-causal, directional, educational logic. | Collapsed by default | static methodology text | No dynamic dependency | Required | Very important | Generally feasible in Streamlit. |  |  |  | Prefer guided step flow over dashboard layout. |  | keep
Page 2 | MVP | 0 | UX | Guided exploration layout | Step flow | see user rout stage column and tab! | Fixed route | N/A | User follows route | Required | Prefer wizard-like sections | Generally feasible in Streamlit. |  |  |  | Prefer guided step flow over dashboard layout. |  | keep
Page 2 | MVP | 6 | Control | Run scenario button | Button | Apply slider/objective/shock settings. | Inactive until inputs valid | session_state inputs | Triggers output refresh | Required | Prevents auto-chaos | Very important UX stabilization. | Without it, app may feel chaotic. |  |  | Good Streamlit-compatible pattern. |  | keep
Page 2 | MVP | 10 | Control | continue to anouther tial (starting stage 3 objective) or Reset button | Button | Return to baseline/defaults. | Visible | session_state defaults | Clears scenario, shocks, comparator if chosen | Required | Must define full vs partial reset | Generally feasible in Streamlit. |  |  |  | Prefer guided step flow over dashboard layout. | I don’t understand your comment!!! | TBD discussion add to tasks
Page 2 | MVP??? | 7 | tracker | track key characters def, descisions (invest) and dimensions change outputs | table index=trial number | [6 empty] | Generally feasible in Streamlit. |  |  |  | Prefer guided step flow over dashboard layout. |  | keep - must!
|  |  |  | overall change index?? | [7 empty] | Generally feasible in Streamlit. |  |  |  | Prefer guided step flow over dashboard layout. | if yes, need development and to add to tables | tbd discuss method and complexity
Page 2 | 1a | 9 | export? | export tracker? |  | export tracker to csv file? | [5 empty] | Generally feasible in Streamlit. |  |  |  | Prefer guided step flow over dashboard layout. |  | keep - top of 2nd priority
Page 2 | Priority 1a MVP as place holder - rule based mvp to be replaced by ai.. | 7 | AI | AI interpretation placeholder | Bottom panel placeholder | Reserved area for future AI-supported interpretation. | Collapsed / clearly labelled TBD | selected scenario state | Could use rule-based placeholder | Optional | AI TBD; not MVP dependency | Correctly limited to placeholder. | LLM hallucination and scope creep. |  | Placeholder only for capstone? | Keep optional and visually secondary. |  | 2nd priority
Page 2 | Priority 1B | 8 | Learning - aI? | Guided reflection mode | Question card | Ask user to reflect before revealing interpretation. | OFF or after first run | reflection_prompt_table | Show prompt after scenario | Optional | Strong educational value | Generally feasible in Streamlit. |  |  |  | Prefer guided step flow over dashboard layout. |  | tbd complexity
Page 2 | Priority 1B | 8 | Learning | Suggested next-step prompts | Prompt chips/buttons | Suggest next exploration step. Including shock recovery strategy.. | Hidden until after run | rule_based_next_step_table | Offer next country/objective/shock | Optional | Rule-based initially | Generally feasible in Streamlit. |  |  |  | Prefer guided step flow over dashboard layout. |  | tbd brainstorm add to tasks

## User_Routes
Page | Page Name | User Route | Lock Status | Open Decision | Assistant Review | Problem / Risk | Missing Info | Decision Required | Advice / Recommendation
Page 1 | Structural Europe Explorer | Landing → Select country → View structural profile → Understand structural family → Explore tradeoff space → Observe pathway trajectory → Compare with another country → Interpret structural tensions → Read assumptions/methodology | Not fully locked | Confirm exact first screen and default country/tradeoff | This tab is now critical. | Architecture drift if routes stay ambiguous. | Exact page-entry logic and first screen. | Freeze routes before new mockups. | Treat this tab as canonical UX flow.
Page 2 | Strategic Tradeoff Sandbox | Select country → Observe current structural profile → Choose reference system → Select strategic objective → Adjust investment priorities → Run directional shift → Observe before/after movement → Apply shocks → Reflect → Reset or re-iterate | Not fully locked | Decide wizard vs dashboard; define shift logic | This tab is now critical. | Architecture drift if routes stay ambiguous. | Exact page-entry logic and first screen. | Freeze routes before new mockups. | Treat this tab as canonical UX flow.

## Formatting_Tasks
Page | Formatting / UX Task | Description | Priority | Assistant Review | Problem / Risk | Missing Info | Decision Required | Advice / Recommendation
Global | EU visual theme | Use EU blue/yellow base; avoid generic SaaS dashboard look | Required | Good operational discipline layer. | Can drift during implementation. | Component-level visual standards. | Decide if wireframe system is needed. | Avoid generic BI-dashboard aesthetics.
Global | MVP markers | Use red star only for true MVP components in mockups | Required | Good operational discipline layer. | Can drift during implementation. | Component-level visual standards. | Decide if wireframe system is needed. | Avoid generic BI-dashboard aesthetics.
Global | Priority markers | Use subtle gold outline/dot for Priority 1, not red MVP star | Optional | Good operational discipline layer. | Can drift during implementation. | Component-level visual standards. | Decide if wireframe system is needed. | Avoid generic BI-dashboard aesthetics.
Global | Country/family colors | Apply consistent colors for structural families and selected countries | Required | Good operational discipline layer. | Can drift during implementation. | Component-level visual standards. | Decide if wireframe system is needed. | Avoid generic BI-dashboard aesthetics.
Global | Progressive disclosure | Use expanders/tabs to avoid overload | Required | Good operational discipline layer. | Can drift during implementation. | Component-level visual standards. | Decide if wireframe system is needed. | Avoid generic BI-dashboard aesthetics.
Page 1 | Visual hierarchy | Profile first, then family, then tradeoff, then pathway, then assumptions | Required | Good operational discipline layer. | Can drift during implementation. | Component-level visual standards. | Decide if wireframe system is needed. | Avoid generic BI-dashboard aesthetics.
Page 1 | Chart labels | Every tradeoff chart must include X/Y meaning and quadrant interpretation | Required | Good operational discipline layer. | Can drift during implementation. | Component-level visual standards. | Decide if wireframe system is needed. | Avoid generic BI-dashboard aesthetics.
Page 2 | Step structure | Baseline → objective → sliders → run → before/after → shock → interpretation | Required | Good operational discipline layer. | Can drift during implementation. | Component-level visual standards. | Decide if wireframe system is needed. | Avoid generic BI-dashboard aesthetics.
Page 2 | Buttons | Run and Reset must be explicit; avoid automatic fake simulation | Required | Good operational discipline layer. | Can drift during implementation. | Component-level visual standards. | Decide if wireframe system is needed. | Avoid generic BI-dashboard aesthetics.
Page 2 | Warnings | Show directional/not predictive framing near scenario output | Required | Good operational discipline layer. | Can drift during implementation. | Component-level visual standards. | Decide if wireframe system is needed. | Avoid generic BI-dashboard aesthetics.
global | number near inputs and outputs to easy use=guided flow.. |  |  | Good operational discipline layer. | Can drift during implementation. | Component-level visual standards. | Decide if wireframe system is needed. | Avoid generic BI-dashboard aesthetics.
| relevant sdg decoration? |  |  | Good operational discipline layer. | Can drift during implementation. | Component-level visual standards. | Decide if wireframe system is needed. | Avoid generic BI-dashboard aesthetics.
| flags of archetypes? |  |  | Good operational discipline layer. | Can drift during implementation. | Component-level visual standards. | Decide if wireframe system is needed. | Avoid generic BI-dashboard aesthetics.
| popup why archetypes were chosen? |  |  | Good operational discipline layer. | Can drift during implementation. | Component-level visual standards. | Decide if wireframe system is needed. | Avoid generic BI-dashboard aesthetics.
|  |  |  | Good operational discipline layer. | Can drift during implementation. | Component-level visual standards. | Decide if wireframe system is needed. | Avoid generic BI-dashboard aesthetics.
|  |  |  | Good operational discipline layer. | Can drift during implementation. | Component-level visual standards. | Decide if wireframe system is needed. | Avoid generic BI-dashboard aesthetics.
|  |  |  | Good operational discipline layer. | Can drift during implementation. | Component-level visual standards. | Decide if wireframe system is needed. | Avoid generic BI-dashboard aesthetics.
|  |  |  | Good operational discipline layer. | Can drift during implementation. | Component-level visual standards. | Decide if wireframe system is needed. | Avoid generic BI-dashboard aesthetics.
|  |  |  | Good operational discipline layer. | Can drift during implementation. | Component-level visual standards. | Decide if wireframe system is needed. | Avoid generic BI-dashboard aesthetics.
|  |  |  | Good operational discipline layer. | Can drift during implementation. | Component-level visual standards. | Decide if wireframe system is needed. | Avoid generic BI-dashboard aesthetics.
|  |  |  | Good operational discipline layer. | Can drift during implementation. | Component-level visual standards. | Decide if wireframe system is needed. | Avoid generic BI-dashboard aesthetics.
|  |  |  | Good operational discipline layer. | Can drift during implementation. | Component-level visual standards. | Decide if wireframe system is needed. | Avoid generic BI-dashboard aesthetics.
|  |  |  | Good operational discipline layer. | Can drift during implementation. | Component-level visual standards. | Decide if wireframe system is needed. | Avoid generic BI-dashboard aesthetics.
|  |  |  | Good operational discipline layer. | Can drift during implementation. | Component-level visual standards. | Decide if wireframe system is needed. | Avoid generic BI-dashboard aesthetics.
|  |  |  | Good operational discipline layer. | Can drift during implementation. | Component-level visual standards. | Decide if wireframe system is needed. | Avoid generic BI-dashboard aesthetics.
|  |  |  | Good operational discipline layer. | Can drift during implementation. | Component-level visual standards. | Decide if wireframe system is needed. | Avoid generic BI-dashboard aesthetics.
|  |  |  | Good operational discipline layer. | Can drift during implementation. | Component-level visual standards. | Decide if wireframe system is needed. | Avoid generic BI-dashboard aesthetics.
|  |  |  | Good operational discipline layer. | Can drift during implementation. | Component-level visual standards. | Decide if wireframe system is needed. | Avoid generic BI-dashboard aesthetics.
|  |  |  | Good operational discipline layer. | Can drift during implementation. | Component-level visual standards. | Decide if wireframe system is needed. | Avoid generic BI-dashboard aesthetics.
|  |  |  | Good operational discipline layer. | Can drift during implementation. | Component-level visual standards. | Decide if wireframe system is needed. | Avoid generic BI-dashboard aesthetics.
|  |  |  | Good operational discipline layer. | Can drift during implementation. | Component-level visual standards. | Decide if wireframe system is needed. | Avoid generic BI-dashboard aesthetics.
|  |  |  | Good operational discipline layer. | Can drift during implementation. | Component-level visual standards. | Decide if wireframe system is needed. | Avoid generic BI-dashboard aesthetics.
|  |  |  | Good operational discipline layer. | Can drift during implementation. | Component-level visual standards. | Decide if wireframe system is needed. | Avoid generic BI-dashboard aesthetics.
|  |  |  | Good operational discipline layer. | Can drift during implementation. | Component-level visual standards. | Decide if wireframe system is needed. | Avoid generic BI-dashboard aesthetics.
|  |  |  | Good operational discipline layer. | Can drift during implementation. | Component-level visual standards. | Decide if wireframe system is needed. | Avoid generic BI-dashboard aesthetics.
|  |  |  | Good operational discipline layer. | Can drift during implementation. | Component-level visual standards. | Decide if wireframe system is needed. | Avoid generic BI-dashboard aesthetics.
|  |  |  | Good operational discipline layer. | Can drift during implementation. | Component-level visual standards. | Decide if wireframe system is needed. | Avoid generic BI-dashboard aesthetics.
|  |  |  | Good operational discipline layer. | Can drift during implementation. | Component-level visual standards. | Decide if wireframe system is needed. | Avoid generic BI-dashboard aesthetics.

## Missing_Definitions
Missing Page Definition | Question | Why it matters | answers! | Status | Assistant Review | Problem / Risk | Missing Info | Decision Required | Advice / Recommendation
Default country | Which country opens first? | Needed for reproducible app state | germany | OPEN | Most important architecture tab. | These gaps block reliable implementation. |  | seems that you did not read my answers! Column! | Do not start Streamlit before freezing these.
Default Page 1 tradeoff | Which tradeoff appears first? | Needed for first screen and demo | suggest in separate table - include all and define implementation in steps by mvp, priority etc., add to pririty tasks | OPEN | Most important architecture tab. | These gaps block reliable implementation. |  |  | Do not start Streamlit before freezing these.
Exact MVP tradeoff list | Which 5 tradeoff maps are included? | Prevents visual sprawl | suggest in separate table - include all and define implementation in steps by mvp, priority etc., add to pririty tasks | OPEN | Most important architecture tab. | These gaps block reliable implementation. |  |  | Do not start Streamlit before freezing these.
Page 1 and 2 data exports | Which exact tables feed profile/family/tradeoffs/pathways? | Needed before Streamlit | define - add task to create, | OPEN | Most important architecture tab. | These gaps block reliable implementation. |  |  | Do not start Streamlit before freezing these.
Page 2 shift logic | What exactly changes when sliders move? | Highest risk; prevents fake simulation | now, when defined rout, build a table | OPEN | Most important architecture tab. | These gaps block reliable implementation. |  |  | Do not start Streamlit before freezing these.
Shock logic | Are shocks numeric, rule-based, or narrative-only? Also shock size, mvp.. | Needed for defensibility | need to define | OPEN | Most important architecture tab. | These gaps block reliable implementation. |  |  | Do not start Streamlit before freezing these.
Reset logic | Full reset or partial reset? | Needed for session_state design | described in features table | OPEN | Most important architecture tab. | These gaps block reliable implementation. |  |  | Do not start Streamlit before freezing these.
Reference toggle | EU average vs comparator country avg only Family later - but family in cards.. Maybe eu map | Controls data schema | yes | OPEN | Most important architecture tab. | These gaps block reliable implementation. |  |  | Do not start Streamlit before freezing these.
Streamlit layout | Tabs, expanders, wizard, or columns? | Must match implementation reality | explain. | OPEN | Most important architecture tab. | These gaps block reliable implementation. |  |  | Do not start Streamlit before freezing these.
AI boundary | Placeholder only vs rule-based summary? | Avoids hallucination/API dependency | described in features table | OPEN | Most important architecture tab. | These gaps block reliable implementation. |  |  | Do not start Streamlit before freezing these.
| based on the updated file, suggest further questions. |  |  |  | Most important architecture tab. | These gaps block reliable implementation. |  |  | Do not start Streamlit before freezing these.

## features + priority+ risks (2)
Feature | Description | MVP P1 | MVP P2 | Priority 1 P1 | Priority 1 P2 | Priority 2 | Future | Project Risk | Demo Value | Analytical Value | Evidence Confidence | Notes
EU-relative normalization | KPI positioning relative to EU average | YES | YES |  |  |  |  | 1 | 3 | 5 | 5 | Core interpretability layer
Absolute/raw toggle | Switch between normalized and raw values |  |  | YES |  |  |  | 1 | 2 | 4 | 5 | Transparency feature
Country selector | Select focal country | YES | YES |  |  |  |  | 1 | 3 | 4 | 5 | Core navigation
Compare 2 countries | Side-by-side comparison | YES | YES |  |  |  |  | 2 | 4 | 4 | 4 | Limit to 2 in MVP
Structural family display | Innovation / Industrial / Adaptive | YES | [5 empty] | 1 | 4 | 4 | 4 | Strong narrative value
Sub-family/archetype display | Country subtype interpretation |  |  | YES |  |  |  | 2 | 4 | 4 | 3 | Slight interpretation risk
Country profile summary | KPI and pathway overview panel | YES | YES |  |  |  |  | 1 | 4 | 4 | 5 | Core user orientation
Tradeoff scatter maps | Growth vs inequality etc. | YES | YES |  |  |  |  | 2 | 5 | 5 | 4 | Core visual grammar
Multi-tradeoff explorer | Select different tradeoff spaces | YES | YES |  |  |  |  | 2 | 5 | 5 | 4 | Core exploratory logic
Time trajectory lines | Historical KPI evolution | YES | [5 empty] | 1 | 3 | 5 | 5 | Strong analytical grounding
Pathway trajectory arrows | Directional structural movement |  |  | YES |  |  |  | 3 | 5 | 4 | 3 | Powerful but riskier
Cluster/topology map | Structural similarity positioning |  |  | YES |  |  |  | 3 | 5 | 5 | 3 | Potential signature visual
PCA topology map | PCA structural embedding |  |  |  | YES |  |  | 4 | 5 | 5 | 3 | Advanced interpretation
UMAP topology | Nonlinear topology embedding | [5 empty] | YES | 5 | 5 | 4 | 2 | Research-grade complexity
Shock toggle system | Apply macro stress scenarios |  | YES |  |  |  |  | 3 | 5 | 4 | 3 | Keep only 2 shocks
Energy shock scenario | Energy stress pathway test |  | YES |  |  |  |  | 2 | 5 | 4 | 4 | Strong Europe relevance
Recession shock scenario | Economic downturn scenario |  | YES |  |  |  |  | 2 | 4 | 4 | 4 | Clear interpretability
Objective selector | Growth / balance / sustainability etc. |  | YES |  |  |  |  | 2 | 5 | 4 | 3 | Core sandbox mechanic
Reference-system selector | Compare to EU/country/family |  | YES |  |  |  |  | 2 | 4 | 4 | 4 | Strong learning mechanic
Investment-priority sliders | Adjust strategic emphasis |  | YES |  |  |  |  | 3 | 5 | 4 | 3 | Central Page 2 mechanic
Before/after comparison | Compare structural states |  | YES |  |  |  |  | 2 | 5 | 4 | 3 | Important learning loop
Re-simulation loop | Multiple iterative trials |  |  |  | YES |  |  | 4 | 5 | 4 | 2 | Complexity rises quickly
Strategy journey tracker | Visualize exploration history |  |  |  | YES |  |  | 4 | 5 | 4 | 2 | Strong educational value
AI interpretation summary | Explain tradeoffs and tensions |  | YES |  |  |  |  | 2 | 5 | 3 | 2 | Major demo value
Guided reflection mode | Delay AI reveal until exploration |  |  |  | YES |  |  | 3 | 5 | 5 | 3 | Strong pedagogy feature
Suggested next-step prompts | AI-guided exploration hints |  |  |  | YES |  |  | 3 | 4 | 3 | 2 | Keep lightweight
Assumptions/methodology panel | Explain limitations and framing | YES | YES |  |  |  |  | 1 | 2 | 5 | 5 | Critical credibility layer
Evidence confidence display | Show exploratory vs robust areas |  |  | YES |  |  |  | 2 | 3 | 5 | 5 | Strong honesty mechanism
Weight sensitivity explorer | Change weighting assumptions |  |  |  |  | YES |  | 4 | 4 | 5 | 2 | Excellent methodology layer
Decision robustness learning | Compare outcomes under assumptions |  |  |  |  | YES |  | 4 | 5 | 5 | 2 | Advanced educational layer
Methodology deep-dive page | Dedicated DA methodology area |  |  |  |  | YES |  | 4 | 3 | 5 | 4 | Possible future Page 3
Energy dependency dimension | Energy resilience indicators |  |  | YES |  |  |  | 2 | 4 | 4 | 4 | Strong addition if simple
Demographic/workforce dimension | Aging/labor structure |  |  |  |  | YES |  | 3 | 3 | 4 | 4 | Slower-moving variable
Structural vs investment dimensions | Separate state vs spending logic | [5 empty] | YES | 5 | 5 | 5 | 2 | Major architecture expansion
Cluster navigation pathways | Bridge/anchor/topology transitions | [5 empty] | YES | 5 | 5 | 5 | 2 | Very ambitious
Worldwide system extension | OECD/global expansion | [5 empty] | YES | 5 | 5 | 4 | 2 | Platform-scale evolution
Educational onboarding | Guided intro/tutorial |  |  |  | YES |  |  | 2 | 4 | 3 | 4 | Strong UX improvement
Export/share results | Save exploration snapshot |  |  |  | YES |  |  | 2 | 4 | 2 | 4 | Useful for demos/presentations
Streamlit storytelling layout | Guided narrative flow | YES | YES |  |  |  |  | 2 | 5 | 4 | 5 | Critical for UX
Interactive topology animation | Animated movement through space | [5 empty] | YES | 5 | 5 | 3 | 1 | Very risky technically